## Summary
Peer Review Summary
Project: | SDK AIF2 LLD review
Review Scope:
Number of Software lines of code added/modified:
List of Supporting Documents:
Base Label or Branch Name or GIT link:
Work Product Author:
Moderator:
Review Meeting(s)
Date: | 2012-02-08
Reviewers: | Albert Bae
General Comments: | See Review log for detail
Status of Review Results
Issues Identified: | 16
Issues Pending: | 6
Issues Corrected | 6
Issues Cancelled: | 3
Issues Deferred: | 1
Modified files: | [list all new and modified files]

## Review Log
Review Log for SDK AIF2 LLD review
Location | Issue Description | Severity | Submitter | Phase of Origin (Optional) | Status | IR# | Remarks
AIF_init.c line 873 | scrambler should be enabled for 8x OBSAI | MAJOR | Albert Bae |  | CORRECTED |  | Code change was made into the LLD. However, as stated in the release notes, WCDMA DL/UL OBSAI is only tested in 4x mode so far. So need to add a test for OBSAI 8x here. We do support/test CPRI 8x though.
AIF_init.c | this code doesn't support GSM and TD-SCDMA | DESIRABLE | Albert Bae |  | DEFERRED | Enter IR # | Right. We have not focused on these modes so far. If customer request these modes, we'll consider how to add them though.
AIF_init.c line 959 | we need to flexibly turn on or off PD, PE link as required by user | DESIRABLE | Albert Bae |  | CANCELLED |  | This is already supported by the LLD. For each link, the LLD configuration object allows the customer to specify the desired number of PE and PD channels. If 0 is specified, then PE and/or PD can be turned off. Note that we also support picking up only a subset of AxCs on a given link.
AIF_init.c line 1020, 1540, 1557 | In case of CPRI, flexible packing mechanism should be supported from PG2.0, so Dbm setup could be modified by user | MAJOR | Albert Bae |  | CORRECTED |  | We understand this is related to the correction of advisory about "AIF2 CPRI LTE Ingress Antenna Carrier Packing Issue". We added support for different packing patterns and also support EDMA-assisted ingress super packet deinterleaving. This last one is a csl utility that we do just at the time we want to check the incoming packets. Currently under test for the support of Lte Cpri relay together with MO configuration.
AIF_init.c line 1047 | cpri8word offset also can be flexibly changed by user for flexible AxC data packing | MAJOR | Albert Bae |  | CANCELLED |  | We see this as a user very specific parameter that can be adjusted in between calls to AIF_initHw() and AIF_startHw() APIs.
AIF_init.c line 1088 | TDD option is turned off. If anyone use this ? | MINOR | Albert Bae |  | PENDING |  | Yes, we only support FDD today with the LLD. We can add LTE TDD support to our plan.
AIF_init.c line 1162 | this code doesn't consider negative Delta, Pi user | MAJOR | Albert Bae |  | PENDING |  | Here, we don't see what the use case is. Please elaborate. We won't support this for AIF2 LLD v1.0.0.0, and we still need a use case from Albert to potentially add this in a subsequent release.
AIF_init.c line 1408 | AxC offset was fixed and that means it doesn't allow flexible external AxC offset in real case. | MAJOR | Albert Bae |  | CANCELLED |  | We see this as a user very specific parameter that can be adjusted in between calls to AIF_initHw() and AIF_startHw() APIs.
AIF_init.c line 1535, 1550 | doesn't support multiple rule pair for one link. | DESIRABLE | Albert Bae |  | PENDING |  | Here, we don't see what the use case is. Please elaborate.
AIF_init.c line 1694 | In case of LTE, Ingress Egress DB buffer depth was fixed to 64 | MINOR | Albert Bae |  | PENDING |  | This enables the support for max 16 AxCs, which we think is enough of the LTE usecase we have seen so far. Please advice if you've seen customers asking for more than that.
AIF_init.c line 1864 | OBSAI users normally may use RP01 interface | MINOR | Albert Bae |  | PENDING |  | Yes, we'll need a plan to add support for this.
AIF_init.c line 1921 | Rad,Ul timer init value can be flexibly modified by user. And DL rad timer was not used | MAJOR | Albert Bae |  | CORRECTED |  | We have support for DL RADT in our latest codebase. The pre-defined values can be adjusted by the customer app after AIF_initHw, prior to effectively starting the AIF2 hardware.
ReleaseNotes_AIF2_LLD.pdf and | Copyright for the documentation would need to have Creative commons text in the first page. Pls see CPPI Release Notes attached. Need this to be resolved before the release hence marking as major. | MAJOR | Raghu Nambiath |  | CORRECTED |  | Docx edited and pdf regenerated.
AIF2-c6670_usersguide.pdf | Same copyright comment as Release Notes | MAJOR | Raghu Nambiath |  | CORRECTED |  | Docx edited and pdf regenerated.
AIF2-c6670_usersguide.pdf | Would probably need to remove section under. Also would need to document single core execution requirement for LLD.////////////////////////// Former doc ////////////////////////////// | MINOR | Raghu Nambiath |  | CORRECTED |  | Docx edited and pdf regenerated.
Test projects | A simple readme for each tests in the same location as Project.txt will be helpful. This could include overview of the test and test execution environment indicating single core. User guide would also need update for different test/example code | DESIRABLE | Raghu Nambiath |  | PENDING |  | Agreed. We already have some explanatory test in the test C file iteself, but to be more user friendly, we'll need to do that later on.
Location | Identifies an associated reference location in the software (e.g., filename, function, module) or document (e.g., chapter, section, paragraph) for the identified issue.
Severity | Identifies the severity of the issue. There are two severity levels: MAJOR and MINOR. A 'MAJOR' defect is one that impacts the final products functionality, quality, performance, supportability, portability, and reusability and most likely will result in a problem that a customer will see. 'MINOR' defects are those that a customer will not see and do not necessarily impact the final product ability to meet functional and quality requirements. ‘DESIRABLE’ defects include modification requests that are optional. This field is optional.
Phase of Origin | Identifies the lifecycle phase where the defect originated for example, if a defect found during a code review is due to misunderstood requirements then the "phase of origin" for this defect is "requirements". The phases are - Requirements, Design, Implementation, Prior/Original Baseline, and Test. This field is optional.
Status | Defines the current state of the issue: PENDING, CORRECTED, CANCELLED, and DEFERRED. The review can only be closed when there are no PENDING issues -- All issues must either be CORRECTED, CANCELLED, or DEFERRED. When an issue is DEFERRED, there MUST be an Incident Report (IR) associated so that the issue can be tracked.
IR# | Identifies the Incident Report (IR) tracking number for any DEFERRED issues

## Code Review Checklist
Code Review Checklist for SDK AIF2 LLD review
The following is a check list intended to be filled out by the author and moderator as part of the code review process. The checklist items represent a collection of best practices gathered from internal lessons learned and best practices from other TI organizations. The intent is to answer each question with a 'YES', 'NO', or 'Not Applicable (NA)' response.
Question | Response | Comment
Has a static analysis tool been run on the software and all identified issues addressed?
Does the code compile with no warnings or error messages?
Does the code meet an approved coding standard?
Have all licensing, copyright, and IP associated with the software been reviewed and addressed? This includes proper copyright statements on all software files
If any of the software is subject to GNU Public License (GPL), has this been addressed according to TI guidelines.
If any of the software is subject to GNU Public License (GPL) v 3.0, has TI Legal approved?
Are all software types used part of an approved coding standard?
Is the associated Design Document approved?
Does the software implementation and API match the design document?
Are all software types used properly to ensure portability?
Is there a valid C-model for all assembly code?
Is there a unit test for the software?
Does the unit test execute on the PC and/or simulator?
Has a peer review been conducted and all major issues resolved?
Has an IR been created to track any remaining issues pending from the code review?
Has the software been compiled for all supported platforms?